## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
| Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
9 | Requirements | scope creep | Scope expands without being properly managed | 3 | 4 | 2 | 1 | Requirements leader and all team members | End of iteration 2 | Keep requirements focused on key features, discuss requirement additions at team meetings before officially adding them to the project | Iteration 1 will be first iteration requiring code deliverable. Scope has been controlled so far. Group is doing well to decide what priorities are. | Open
4 | Communication | duplicate work | Team members independently complete the same documentation or feature | 3 | 3 | 2 | 2 | team leader and all members | end of class | Align with team on some key back-end features at Sunday, 9/23 meeting | No duplicate front-end work. Some duplicate back-end work | Open
11 | Management | improper task assignments | Wrong tasks assigned to wrong team members | 2 | 3 | 2 | 3 | Team leader and all members | end of class | Keep tasks in Jira organized, with clear goals for each team member during each iteration | End of iteration 1, no issues with tasks being assigned to wrong team members so far | Open
8 | Requirements | unclear requirements | Features are not described in explicit detail. Not enough information to begin implementation | 2 | 4 | 2 | 6 | Requirements leader and all team members | middle of iteration 1 | Send out user surveys to gain insight into potential features. Discuss and refine requirements in meetings during weeks 1 and 2 | End of iteration 1, requirements are clear and detailed. | Open
12 | Management | improper planning | Ineffective meetings, missing key deliverables, unclear project direction | 3 | 4 | 3 | 7 | All | end of class | Meetings will happen Thursdays after class and Sunday evenings to review current project direction/status and tasks for the week | Deliverables have been on time as of end of iteration 1. The group as a whole is functioning well to achieve deliverables and plan for future iterations. Meetings are productive | Open
13 | Management | lack of management skills | Let's be real, we're not C-suite executives. Unless you are, in which case my apologies! | 4 | 4 | 4 | 8 | All | end of class | Do our best! Communicate constantly, be respectful, open, and honest | Team is working well together to control scope and manage distribution of responsibilities. No management issues | Open
10 | Requirements | constant requirements changes | Requirements are updated repeatedly as new features are discussed/desired | 1 | 2 | 2 | 9 | Requirements leader and all team members | middle of iteration 1 | Cement base requirements during weeks 1 and 2. Develop plan for introducing future requirements changes. | Requirements are stable | Tentative completion
14 | Technology competence | Not familiar with the framework used | Using Spring Boot and React | 2 | 2 | 2 | 11 | Design/Implementation Leader, security leader and all team members | End of iteration 1 | Team members can research Spring Boot in general, and from the perspective of their assigned area, be it config, testing, security, data model/design, etc... | Towards the end of iteration 1, all team members have been researching and are up to speed with project technologies. | Open
5 | Communication | worked on wrong components | Tasks were not detailed enough, work completed for wrong area of the project | 2 | 4 | 3 | 12 | All | End of iteration 1 | Use team meetings and Jira tasks to ensure that everyone's responsibilities are clear | No issues so far | Open
7 | Communication | inconsistent work | Variable output from week to week | 3 | 3 | 3 | 13 | All | end of class | Check in during team meetings, make sure everyone has support if life comes up or if that week's tasks are particularly time consuming. | No issues so far | Open
15 | Technology competence | Not familiar with the programming language used | Using Java | 1 | 4 | 3 | 14 | All team members | middle of iteration 1 | Research Java from perspective of assigned area if necessary | No data yet | Open
18 | Technology competence | Not familiar with Git |  | 1 | 4 | 2 | 15 | Configuration leader and all team members | Start/middle of iteration 1 | Lab1 will help us become familiar. Discuss git usage (branching, commits, etc..) during week 1 and 2 meetings if possible. | In progress | Open
17 | Technology competence | Other technology unfamiliarity |  | 1 | 2 | 1 | 16 | Configuration leader and all team members | End of iteration 0 | Confirm tools to be used during project, research any that we're unfamiliar with | In progress | Open
3 | Personnel | Lack of motivation or responsibility | One or more team members have not been given engaging or important tasks | 1 | 4 | 3 | 17 | All team members | end of class | Check in each week with each team member. How are your tasks going? Is there enough to do? Do you need support? | No issues so far | Open
6 | Communication | useless work | Work unrelated to project | 1 | 2 | 1 | 20 | All | End of iteration 0 | Discuss planned tasks together, update Jira to reflect current priorities | No issues | Open
2 | Personnel | add new team members |  | 1 | 2 | 2 | 30 | All team members | 2023-09-11 | Redefine scope and split current tasks if necessary | No one added yet | Open
1 | Personnel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | team leader and all members |  | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
16 | Technology competence | Not familiar with unit testing | [5 empty] | QA leader/security leader and all team members |  |  |  | Open
19 | Design and implementation | Improper design | [5 empty] | Design/Implementation Leader and all team members |  |  |  | Open
20 | Design and implementation | improper technology stack | [5 empty] | All |  |  |  | Open
21 | Design and implementation | Messy code | [5 empty] | QA leader and all team members |  |  |  | Open
22 | Testing | Not enough testing | [5 empty] | QA leader/security leader and all team members |  |  |  | Open
23 | Integration and deployment | Not enough time for integration and deployment | [5 empty] | All |  |  |  | Open