## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Any other metrics defined in your SPPP
0 | 09/05-09/14 | - Project planning and set up - Set up requirements, risk management plan, QA plan, and configuration plan | None | - Team has decided on all tools that will be used, some of which are new to certain members of the team and those members plan to familiarize themselves in the coming weeks/iterations | - For next iteration, we will set up the story and distribute it to each memebers | 0 | 0 | 0 | 0 | 0 | 46.5 | 50.5 | 4 | 17 | 6.5 | 2 | 0 | 0 | 8 | 8.5 | 4.5
1 | 09/15-09/26 | - Begin setting up the database - Begin creating pipeline - Begin creating authentication - Completed SDD - Completed STD | Deciding how to proceed with Authentication | - Team was sub-broken into front end team and back end team, each team then decided on certain approaches that team members planned to familiarize themselves with | - Have regular meetings to check in on code progress for all team members - Have multiple team members check to ensure they can access the different tools being used to set the project up |  | 5 |  |  |  | 52 | 52 |  | 23 | 6 | 9.5 | 4 | 1 | 3.5 | 0 | 5
2 | 09/27-10/10 | - Created endpoints for front end to access database - Created functionality code in backend that enables our core features - Decided on authentication and began working that into the program - Decided on front end framework (MUI) - Began creating components for UI - Created pipeline - Created container - Decided on using Hiroku as our hosting tool - Connected Hiroku to backend - Created and tested dashboard, set up, navigation, add expense, and add income components | - With team members beginning to access code from other areas of the program, the team had to communicate across front end and back end teams to ensure that all of the needed endpoints were accessible. - Additionally, due to the combination of front end and back end progress, the team had to work together to create new endpoints for certain requirements and had to communicate more with different members to ensure the front end could communicate properly with the backend. - Since we need to have the application hosted for the final iteration, the team needed to find a hosting tool and ensure that it would integrate with our setup without having to invest too much time to ensure other application requirements were met |  | - Integrate the Hiroku hosting with the front end for the final iteration - Continue testing components to ensure database is updated for particular users - Finalize the notification feature that will monitor expense categories and alert users when a category has exceeded a determined limit | 4 | 4 |  | 3 |  | 76.5 | 76.5 |  | 19 | 2.5 | 6.5 | 26.5 | 7 | 8 | 0 | 7
3 | [10 empty] | 79 | 79 |  | 16.5 | 3 | 10 | 16 | 12 | 9 | 1 | 11.5

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Chaitanya Saraogi
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/11 | 4 | 4 | 0 | 0 - learn git and project management requirements 5 - meet with Jisoo and communicate over Discord 6 - set up git | 2 |  |  |  |  | 1 | 1 |  | Was part of team 7 which got diluted and was moved to team 1 | Was part of team 7 which got diluted and was moved to team 1 | Intigrated with team 1, read and aligned with team docs | 1 definere quirements and set up stories in Jira | 6
2 | 09/12 - 09/18 | 6 | 5 | 1 | 0 - learning Rest api, spring boot 1 - Created User stories and acceptance criterias | 2 | 3 | [6 empty] | Created user stories, acceptance criteria and Tasks for Expense tracking | none | Na |  | 10
3 | 9/19 - 09/25 | 11 | 9 | 2 | 0 - learn Database; Learn cucumber testing 1 - Work with the team to plan high-level architectural design of project 2 - Created design patterns to be implemented 5 - communication with team and meetings; up the timeline for our requirements 7 - Updated documentation, created and presented Iteration 1 | 3 | 1 | 2 |  |  | 1 |  | 2 | Design pattern | none | na | Start implementation of budget notification system | 10
4 | 9/25- 10/02 | 10.5 | 8 | 2.5 | 0 - learn Database; Learn cucumber testing 1 - Work with the team to plan high-level architectural design of project 3- started working on budget notification system 5 - communication with team and meetings; up the timeline for our requirements 7 - Updated documentation | 2 | 1 | 0 | 4 | 0 | 1.5 |  | 0.5 | Budget notification system and testing | 1. errors not letting compile | reviewed code with team and found imports missing | finsish budgeting notifications system and start on testing | 10
| 10/03- 10/10 | 11.5 | 9 | 2.5 | 0 - learn Database; Learn cucumber testing 1 - Work with the team to plan high-level architectural design of project 3- working on budget notification system 4- creating tests for budget notifcation 5 - communication with team and meetings; up the timeline for our requirements 7 - Updated documentation | 2 | 1 | 0 | 5 | 1.5 | 1.5 | 0 | 0.5 | Budget notification system and testing | working on testing will merge with dev branch after | implementation completed, working on creating tests | finish testing. see if team wants to add budgeting option by category | 10

## Sean Rawson
Sean Rawson
Your Lead Roles: Security leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/11 | 4 |  |  | 0 - Learn about Git, research software security best practices 1 - Plan initial non-functional security requirements SPPP section 3b 5 - Fill out initial risk assessment sheet and SPPP section 4b 6 - Research code standards, possible linting or static analysis tools | 2 | 0.5 | 0 | 0 | 0 | 1 | 0.5 | 0 | SPPP section 3b SPPP section 4b SPPP risk management initial draft Commit bio to lab1 git branch | 1. Not very experienced with software security 2. I need to flesh out security standards for the project in more detail | 1. Progressing decently, learning about Spring Security, authentication, and authorization 2. Will discuss security at next team meeting | 1. Continue learning about spring security, establish core security-related features that are necessary vs. nice-to-haves 2. Help start backend implementation, including basic database operations 3. Time permitting - Begin test implementation of user registration | 4
2 | 09/12 - 09/18 | 8.5 |  |  | 0 - Research Spring Security authentication, JWT generation and use 2 - Plan initial security design 3 - Create authentication endpoint 5 - Discuss high-level architecture with team | 4 | 0 | 2 | 2 | 0 | 0.5 | 0 | 0 | No deliverables this week | 1. Spring Security has a lot of parts, research takes a while 2. Some security-related aspects of the project are still unclear | 1. Continue researching and refining authentication and authorization features 2. Discuss SSL certs at next meeting | 1. Implement JWT validation 2. Implement endpoints for adding income and expenses | 8
3 | 09/19 - 09/25 | 11.5 |  |  | 0 - Continue learning about authentication and proper JWT use 2 - Work with team to plan high level architectural design of project 3 - Implement several user and expense related endpoints 4 - Write first unit tests 5 - Meet with Sherif to discuss authentication, coordinate with team regarding iteration 1 presentation | 4 | 0 | 2 | 4 | 0.5 | 1 | 0 | 0 | SDD security section update SPPP risk management iteration 1 demo/presentation | 1. Some technological issues on my side in team meetings 2. Authentication mechanism not decided, two options currently | 1. Video sharing issue solved already 2. Will decide between auth options at Sunday, 9/24 meeting | 1. Continue implementation of endpoints 2. Move forward with authentication system development 3. Discuss communication between front and back-end components with team | 10
4 | 09/26 - 10/02 | 10 |  |  | 2 - Design user overview endpoint to support UI dashboard 3 - Refine API endpoints and add additional ones as needed to support front end functionality 4 - Write unit tests for main back end classes 5 - Group meetings/discord communication | 0 | 0 | 3 | 3 | 3 | 1 | 0 | 0 | No deliverables this week | No issues | No issues | 1. Help integrated authentication code with existing back end 2. Continue writing unit tests | 8
5 | 10/3 - 10/9 | 12 |  |  | 0 - Learn about JPA interaction with composite primary key tables 2 - Design classes and database table for expense category budgets in preparation for iteration 3 3 - Implement date range searches for expense, income, and user overview endpoints 4 - Continue filling out unit tests for the back end 5 - Assist in testing efforts for planned expense notification functionality, communicate with team about database updates | 1 | 0 | 3 | 4 | 3 | 1 | 0 | 0 | Updated SPPP risk management spreadsheet Personal progress report | No issues | No issues | 1. Help integrate front end with back end 2. Perform testing to ensure that authentication functionality integrates well with back end 3. Add expense category budgeting options to back end | 10

## Clyde Yeung
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles:Configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/11 | 8 | 8 | 4 | 0 - learn sprintboot 1 - breakdown requirements, 2 - design pipeline and containers 6 - set up git, google drive, JIRA, research SonarQube and OpenLDAP 7 - research similar products, prepare presentation | 4 | 2 | 2 |  |  | 3 | 4 | 1 | 1. Write 2 documents contribute to the configuration sections of SPPP 2. Set up the intial git, commit a test message on git, set up the branches. 3. Set up JIRA, wrote the features and stories according to the SPPP 4. Participate in Iteration 0 presentation, added the slides for configuration/pipeline/git 5. Create container tutorial for team members | 1. learning springboot as I have never used that before. 2. Researching using Sonarcloud to minimize time to create containers 3. Researching OpenLDAP 4. Learning MariaDB to set up the intial DB container 5. Checking how GitHub Action would be working with the different stages | 1. finish springboot training in 2 weeks. Should be able to help bug fixing and may be create features 2. Creating containers and set up the inital pipeline | 0 - continue to learn springboot 2 - continue to design the pipeline and decide on SonarCloud, linter and OpenLDAP 3 - Frist pipeline (github action) created 3 - Create the MariaDB container 3 - Create the basic App container 5 - Work with Sherif to have a dummy project to test build | 12
2 | 09/12 - 09/18 | 15 | 15 | 2 | 0 - learn github action, mariadb, 2 - design the container 2 - design how to deploy the container(s) 7 - research code scanning tool | 8 |  | 4 |  |  |  |  | 3 | 1. Resaerch code scanning tool. Will probably use sonar cloud 2. Learn github action 3. Learn mariadb setup 4. Set up the mariadb container
3 | 09/19 - 09/25 | 25 | 23 | 2 | 0 - learn how to create war file 3 - set up the actual mariadb container 3 - set up the pipeline using github action 3 - set up the application container 3 - Implement the deployment using docker-compose 4 - testing the deployment (try to create user) 5 - work with Searn to understand the end point for testing the deployment 7 - Resarch about the difference of war and executable jar. and other issues during the implementation | 3 |  |  | 15 | 1 | 3 |  | 3 | 1. Set up the trigger to kick off the pipeline 2. Set up the pipeline to build the pennywise application 3. Create the war file 4. Set up the pipeline to create the application container with pennywise deployed 5. Use docker-compose to launch the containers | 1. After checking with Sean, we will have to use the executable jar for deployment instead of war 2. We wil neet to set up the cert so the connection is https 3. Need to find a way for using the credentials | 1. Will need to rework the applicaiton deployment. 2. Need to work with Sean and Sherif for the security and cert 3. Need to implement the code scanning and linting | 1. Finish the code scanning using sonar cloud 2. Finish setting up the applications containers 3. Work with Mali to implement the testing stage 4. Implement the stage to upload the "zip" so people can download the application 5. Write up documentation how to run the containers | 25
4 | 09/26-10/2 | 20 | 18 | 2 | 0 - learn about render as Yuting suggested 6 - Merging branches to keep code 7 - Investigate why upload to google drive stoopped working 7. Investigate using Render as a new platform to deploy | 7 |  |  |  |  | 2 | 1 | 10 |  |  | 1. Investigate uploading zip file to google drive stopped working - abandon using this method 2. Trying to switch to use Render as Yuting suggested 3. Determined Render is not a good platform for our project 4. Switch to Heroku | 1. Learn Heroku and how the platform works | 30
5 | 10/3-10/9 | 30 | 27 | 3 | 0 - learn Heroku platform 2 - design how to deploy to Heroku 3 - set up the backend deployment to Heroku 3 - set up the application container 3 - Implement secret for deployment 4 - testing the deployment 5 - work with Jisoo/mali/Sean on the front end deployment and the backend 6 - Configuring MariaDB on Heroku 7 - Investigate build pack issues 7 - investigate different DB addon. | 8 |  | 5 | 4 | 4 | 3 | 2 | 4 | 1. Switched to deploy to Heroku as google drive failed working 2. Set up new action to accomodate the change 3. |  | 1. Need to resolve the port number for backend (Heroku assigns random #) - resolved 2. Heroku offers many ways to deploy and have to pick out the right method 3. git structure need to accomodate (as build pack does not work with sub folders) - resolved 4. Mainly on debugging the deployment as Heroku throws deployment errors for the back end - resolved | 1. Deploy Front End 2. Work with Front end team to hook up bankend endpoint in production environment 3. Work with database for changes Sean requested | 25

## Mali Rivera
Mali Rivera
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/11 | 7 | 5 | 2 | 0 - learn springboot and integration testing 1 - define high level plan for QA testing, 5 - make QA plan 6 - set up git 7 - research similar products, prepare presentation | 2 | 0.5 |  |  |  | 1 | 0.5 | 1 | 1. Write QA section of SPPP 2. Set up git, commit bio to Lab1 branch 3. Prep slides and speaking point for 0 presentation | 1. not familar with Spingboot framework 2. new to integration testing but excited to learn about it | 1. research spring boot and integration testing | 0 - continue to learn Spingboot 1 - continue to define requirements 3 - research linking Java and React application | 6
2 | 09/12 - 09/18 | 7.5 | 5.5 | 2 | Individual Task Breakdown 0 - research how to populate pie chart in react, continue to learn spring boot framework 2 - work with front-end team on UI design 4 - work on STD testing sections 7 - practice mockMVC and mockito testing | 2 |  | 0.5 |  | 1 |  |  | 2 | 1. Write QA sections of STD 2. complete Lab 2 (add user stories to Jira) 3. practice pulling data and creating charts in Chart.js | 1. not familiar with mockMVC or mockito 2. not familiar with react spring boot integration | 1. watch youtube tutorials on mockMVC and mockito 2. research reacts spring boot integration | 0 - continue to learn testing frameworks 1 - research react spring boot integration 3 - research authentication options with react | 6
3 | 09/19 - 09/25 | 7.5 | 5.5 | 2 | Individual Task Breakdown 0 - learn mockMVC, mockito, Cucumber, research authentication (JWT vs Oauth) 2 - work on UI design 3 - implement developmental chart logic 4 - write integration test when code is available. fill out STD sections 7 - unclassified | 2 |  | 0.5 |  | 1 |  |  | 2 | 1. Write QA sections of STD 2. prep and participate in presentation iteration 1 | 1. have to wait on back end team to write integration tests | 1. add more unit and integration tests this week | 0 - continue to learn testing frameworks 1 - write integration/unit tests 3 - implement front-end functionality | 6
4 | 09/26-10/2 | 12 | 10 | 2 | Individual Task Breakdown 0 - Learn Material UI, Chart.js, mockMVC, and mockito, learn how to integrate spring boot and react 3- Work on Dashboard.js, NavBar.js, ExpenseChart.js and ExpenseTable.js 4 - Write Integration tests 5 - help communicate how to run project locally, and access backend on front-end | 4 |  |  | 3 | 2 |  |  | 1 | 1. write Lab 3 code 2. write integration tests 3. enabled CORS configuration so that front-end can access code | 1. not familiar with integrating back end and front end and working with local databases 2. not familiar with spring boot so have to research controller vs. service vs. mapper to be able to write tests | need to research more about spring boot and react integration, and also integration testing with spring mock MVC | 0 - continue to work on back end and front end integration 1 - work on front-end implementation of user stories 3 - write tests | 10
5 | 10/3-10/9 | 14 | 12 | 2 | Individual Task Breakdown 0 - learn Material UI, Chart.js, mockMVC, and mockito 3- Integrate back and front end, add logic to create a map of user expenses by expenseCategory, pull data in front-end, check posting data updates charts in real time, add integration tests, create demo for front-end slides 4 - write Integration tests, write STD sections, create Testing Metrics Report, create Testing Slides for presentation 5 - help communicate how to run project locally, and access backend on front-end | 4 |  |  | 5 | 2 |  |  | 1 | 1. code (Dashboard.js, ExpenseChart.js, ExpenseTable.js, NavBar.js, Integration tests) 2. create Testing Metrics Report, Testing slides, STD update, and script testing slides, record front-end demo | we're having issues with login functionality which affects the implementation of the rest of our program | need to figure out a login plan with the team, add date filtering capability to dashboard, edit the UI design, make sure we have all the functinoality that we wanted and continue to write tests | 0 - continue to work on back end and front end integration 1 - finish up front-end implementation 3 - continue to test, study for final | 13

## Sherif Zeyada
Sherif Zeyada
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Wrote out high level requirements proposal for SPPP | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
2 | 09/12 - 09/18 | 8.5 |  |  | 0 - Research Google Oauth2 2 - Plan initial Google Oauth2 3 - Create Google confidentail 5 - Discuss high-level architecture with team | 4 | 0 | 2 | 2 | 0 | 0.5 | 0 | 0 | No deliverables this week | 1. Spring Security has a lot of parts, research takes a while 2. Some security-related aspects of the project are still unclear | 1. Continue researching and refining authentication and authorization features 2. Discuss SSL certs at next meeting | 1. Implement JWT validation 2. Implement endpoints for adding income and expenses | 8
3 | 09/19 - 09/25 | 11.5 |  |  | 0 - Continue learning about google authentication and spring security 2 - Work with team to plan high level architectural design of project 4 - Write first unit tests 5 - Meet with Saan to discuss authentication, coordinate with team regarding iteration 1 presentation | 4 | 0 | 2 | 4 | 0.5 | 1 | 0 | 0 | SDD Design and database | 1. Some technological issues on my side in team meetings 2. Authentication mechanism not decided, two options currently | 1. Video sharing issue solved already 2. Will decide between auth options at Sunday, 9/24 meeting | 1. Continue implementation of endpoints 2. Move forward with authentication system development 3. Discuss communication between front and back-end components with team | 10
4 | 09/26 - 10/02 | 10 |  |  | 2 - Design user overview endpoint to support UI dashboard 3 - Refine API endpoints and add additional ones as needed to support front end functionality 4 - Write unit tests for main back end classes 5 - Group meetings/discord communication | 0 | 0 | 3 | 3 | 3 | 1 | 0 | 0 | No deliverables this week | No issues | No issues | 1. Help integrated authentication code with existing back end 2. Continue writing unit tests | 8
5 | 10/3 - 10/9 | 12 |  |  | 0 - Learn about React 2 - Design the integration between the Frontend and backend google Oauth 4 - Continue filling out unit tests for the back end 5 - Assist in testing communicate with team about database updates | 1 | 0 | 3 | 4 | 3 | 1 | 0 | 0 | Updated SPPP risk management spreadsheet Personal progress report | No issues | No issues | 1. Help integrate front end with back end 2. Perform testing to ensure that authentication functionality integrates well with back end 3 | 11

## Brian Fenstermacher
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/11 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write SPPP section 1 and 2 2. Wrote overfiew of all possible features for application 3. Created starting point for slide deck 4. Participate in iteration 0 presentation 5. Worked with clyde to merge our first pull request to the master branch in Github | 1. not familiar with springboot, working on learning 2. planning to learn more about React to help with front end | 1. go through a few tutorials on both to build a baseline understanding before diving too deeply into working with them in our project | 0 - continue to learn springboot & react 1 - begin looking into how to integrate react with our project 3 - work out very basic HTML with Mali to have for our frontend | 6
2 | 09/12 - 09/18 | 6 | 4 | 2 | 0 - learn REACT and how to integrate with Java, learn how to set up user stories and acceptance tests with Jira 1 - wrote 2 primary functionality user stories and 4 total acceptance tests 5 - broke our team into front end/back end groups to better manage the progress and make better use of time, led meetings to ensure all topics were covered and team feels prepared and comfortable regarding their action items | 1.5 | 1.5 | 0 | 0 | 0 | 1 | 0 | 0 | 1. Wrote 2 user stories and added to JIRA 2. Wrote 2 acceptance tests per user story and added them to JIRA 3. Found resource to help front end team, myself included, better understand REACT's relation to Java | N/A | N/A | 0 - continue familiarization with REACT, create practice project on local machine to better familiarize with what we're working on 3 - begin figuring out what endpoints will be needed for the front end, and create a prototype to better see what our setup will look like | 5
3 | 09/19 - 09/25 | 7 | 5 | 2 | 0 - learn about front end architecture, learn more about utilizing databases 1 - assign SDD and STD sections to relevant team leads, decide on focus areas for iteration 1 deliverables 3 - Created interactive UI prototype to better define what endpoints the front end team will need 4 - Presented prototype to team, received feedback on functionality and reworked prototype to ensure all features were accounted for 5 - led team meetings to ensure all topics were covered and team members feel prepared and comfortable regarding theiraction items | 1.5 | 0.5 | 0 | 1.5 | 1 | 0.5 | 0 | 0 | 1. Created interactive prototype for UI design portion of SDD 2. Shared resources to front end team that illustrated the connection between React and Java | 1. Not entirely sure about front end architecture and how to ensure that our project is implementing that in the best way possible | 1. Continue reading and researching about front end architecture | 0 - Read about using endpoints in VSCode, learn more about the chart plugin we intend to use to showcase budgeting on front end. 2 - Using the front end architecture that we've found, begin deciding how our particular project will break into that layout 3 - Begin writing structural code for the front end 5 - Continue leading discussions and ensuring that team members know what objectives we are trying to accomplish 6 - Ensure that we have a universal staging environment that we can all reference and see how the project is progressing | 6
4 | 09/26 - 10/2 | 11 | 8 | 3 | 0 - Learn about postman, docker, material ui, accessing endpoints, creating local environment for development 1 - Bi-weekly code checkins to ensure progress is being made and team members feel comfortable about their workload 2 - Using components from MUI, designed the layout for the add-expense and add-income pages 5 - Created outlines for each of our meetings, checked in with all team members at each meeting to see how progress is coming along, ensured that team members feel comfortable with their workload | 2 | 1 | 4 |  |  | 1 |  |  | 1. Learned how to work with MUI and began creating the AddIncome and AddExpense pages | 1. Overall very unsure about a lot of the programs that we're using so a bulk of time this week was spent learning how to use those and work with them efficiently | 1. Continue learning about these programs and work with a couple of small examples to familiarize myself before applying that information directly to our working project | 0 - continue learning about pipeline, docker, and mariaDB 3 - create the AddIncome and AddExpense components 5 - continue leading meetings and checking in with team members 6 - plan to successfully set up a local environment for testing | 11
5 | 10/3 - 10/9 | 14.5 | 11.5 | 3 | 0 - Continued learning Docker and MUI 1 - Wrote Readme.md file to outline how to use the application + Reviewed SPPP and provided comments on all features that have had progress made for this iteration 2 - Continued designing the layout for the AddExpense and AddIncome pages 3 - Commited AddExpense and AddIncome components to working branch 5 - Created outlines for each meeting, checked in with team members, led meetings 6 - Was able to successfully create a local environment | 2 | 3 | 4 | 0.5 |  | 1 | 1 |  | 1. Created the AddIncome and AddExpense components 2. Wrote readme file and updated SPPP document to cover progress 3 - Finished creating the AddIncome and AddExpense 4 - Ensured that the two components were working locally 5 - Continued leading meetings and ensuring that we had an outline to reference for meetups 6 - Set up local environment and was able to run docker |  |  | 0 - continue learning about the pipeline and Hiroku for our final iteration 3 - Finalize the AddIncome and AddExpense to ensure it is working properly 5 - continue leading meetings | 11.5

## Jisoo Lee
Jisoo Lee
Your Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/11 | 6.5 | 4.5 | 2 | 0 - learn git and project management requirements 1 - define high level requirements and priorities using user survey 5 - propose project scheme, make a user survey 6 - set up git 7 - iteration0 presentation | 1 | 1.5 | 0 | 0 | 0 | 1 | 0.5 | 0.5 | 1. Write SPPP section 8a and 9a 2. Created budgeting app user survey 3. Commit bio to lab1 git branch 4. Participate in recording presentation for iteration0 5. Participate in making Epics/sub-tasks in Jira | 1. not familar with project management requirements 2. project planning consumed some time and effort | 1. Not familiar with requirement role, so worked on learning the how to set up priorities and requirements. | 1 - continue to define requirements and set up stories in Jira and acceptance test 2 - work with Sherif with designing engines for our app 6 - set up Docker container | 6
2 | 09/12 - 09/18 | 5.5 | 4 | 1.5 | 0 - Research on acceptance test set up (Cucumber in Java) 1 - Set up Jira stories and sub tasks 5 - Discuss high-level architecture with team 6 - Set up Docker | 1.5 | 2 | 0 | 0 | 0 | 1.5 | 0.5 | 0 | 1. Jira stories and subtasks set up | 1. Cucumber test was not familiar at first, but documented on the STD. 2. Undertand how to implement React with Java application. | 1. Continue to work on requirement role, after we start coding I will set up Cucumber test | 1 - Check story and requirement status for our team 5 - Work with Brian and Mali on front-end | 6
3 | 09/19 - 09/25 | 5.5 | 4 | 1.5 | 0 - Continue learning on front end set up and mock ups 1 - Updated accepatance test for requirements and set up the timeline for our requirements 2 - Work with team to plan high level architectural design of project 5 - Meet with Brian and Mali with front-end. Regular meeting with whole team to ensure design for full stack application | 1.5 | 1.5 | 1 | 0 | 0 | 1.5 | 0 | 0 | 1. Write SDD introduction part 2. Write STD acceptance test part 3. Updated SPPP User stories 4. Updated Jira story timeline | 1. Had to update timeline on Jira for viable plans for our app. 2. Need to work on real design of UI and itegration with the backend. | 1. Continue to check on status of our requirements and acceptance tests | 1- Update acceptance tests for our engines/codes 1 - Update SPPP requirements and STD accpetance test 2 - Team work with front-end design 6 - Set up VScode, React libraries | 6
4 | 09/26 - 10/02 | 10.5 | 8 | 1.5 | 0 - Continue learning Google Oauth in Javascript 1 - Updated accepatance test for requirements and set up the timeline for our requirements 3 - Work on the front end, user set up page 4 - Work on Lab3 test on Javascript code 5 - Meet with Brian and Mali with front-end. Regular meeting with whole team to ensure design for full stack application 5 - Set up VScode, intall Node.js and React. Distributed pages for the frontend team. | 1.5 | 1 | 0 | 2 | 3 | 1.5 | 0 | 0 | 1. Testing javascript for Lab3 2. Install Node.js React app and created pages. 3. Updated Jira status | 1. Installing React app and integrating with backend required a lot of communication 2. Need to work with backend team with the Google Oauth | 1. Continue to work on Google Oauth process in frontend | 1- Update status in Jira 1 - Update SPPP and STD accpetance test 2 - Team work with front-end design 3 - Write code for SetUp page and Login page 4 - communicate with backend for checking endpoints for REST APIs and work with conficurations set ups for deploying
5 | 10/03 - 10/09 | 13.5 | 9 | 1.5 | 0 - Continue learning Google Oauth in Javascript 1 - Updated Jira time line 3 - Work on the front end, updating user set up page and Google Oauth 4 - Testing whether it is integrated with backend. 5 - Meet with Brian and Mali with front-end. Regular meeting with whole team to ensure design for full stack application, presentation recording for iteration2 | 1.5 | 1 | 0 | 3 | 4 | 2.5 | 0 | 0 | 1. Write code for Sign-in folder (SetUp.js, Auth.js, Login.js, OauthRedirect.js, PostToken.js) 2. Check endpoints for REST APIs with backend team and updated the codes 3. Presentation for interation2 mock up video for frontend | 1. Integration with backend required loads of communications for updating bugs 2. Need to work on Google Oauth with back end team | 1. Continue to work on Google Oauth process in frontend | 1- Update status in Jira and check the progress 1 - Update SPPP and STD 2 - Team work with front-end design 3 - Write code for user name set ups when Google Oauth is ready 4 - communicate with backend for checking endpoints for REST APIs and work with conficurations set ups for deploying