## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
| Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
23 | Integration and deployment | Not enough time for integration and deployment |  | 4 | 4 | 3 | 1 | Build/config leader and all | End of class | All current code will be merged into dev branch, with any new code being developed on feature branches. This wll allow for a consistent dev build for integration testing and deployment testing. | Taken on by config leader. In progress, with potential deployment to Heroku. | Open
19 | Design and implementation | Improper design | Poor architectural decisions leading to implementation, security, and reliability issues | 4 | 4 | 4 | 2 | Design/Implementation Leader and all team members | End of iteration 2 | Do what we can until the end of iteration 2. For iteration 3, it's too late to make major design changes. | There are a few issues with our design, but the team has managed them by controlling scope and being realistic about what can be included for each iteration. | Open
22 | Testing | Not enough testing | self-explanatory | 3 | 3 | 3 | 3 | QA leader/security leader and all team members | End of iteration 3 | Continue writing unit and integration tests through iteration 3. Increase branch coverage as high as possible. | Unit test coverage around 85% currently. Integration testing and branch coverage for unit tests will be the iteration 3 focus. | Open
16 | Technology competence | Not familiar with unit testing | Self explanatory | 2 | 2 | 3 | 4 | QA leader/security leader and all team members | End of iteration 3 | Review testing methodologies and testing metrics. Collaborate on testing when necessary. | Some issues with testing, but the team is working through them together | Open
11 | Management | improper task assignments | Wrong tasks assigned to wrong team members | 2 | 3 | 2 | 5 | Team leader and all members | end of class | Keep tasks in Jira organized, with clear goals for each team member during each iteration | Tasks have not been assigned to the wrong team members, but tasks in Jira aren't organized by iteration. Need to clean up Jira and align tasks with iterations. | Open
21 | Design and implementation | Messy code | This code needs to clean up its room and take a shower | 3 | 3 | 2 | 6 | QA leader and all team members | End of iteration 3 | Refactor when necessary. Use Sonarqube for quality scanning | With such a tight timeline, some messy code is expected. Unit testing and clean-as-we-code practices will be important in maintaining as clean a codebase as possible. | Open
12 | Management | improper planning | Ineffective meetings, missing key deliverables, unclear project direction | 3 | 4 | 3 | 7 | All | end of class | Meet frequently and stay in contact over discord to align on key deliverables in remaining iterations. | Deliverables have been on time as of end of iteration 1. The group as a whole is functioning well to achieve deliverables and plan for future iterations. Meetings are productive | Open
14 | Technology competence | Not familiar with the framework used | Using Spring Boot and React | 2 | 2 | 2 | 8 | Design/Implementation Leader, security leader and all team members | end of class | Team members who are more familiar with the frameworks should collaborate and provide assistance when they can. | This risk will likely remain open through the end of the class, due to the shortened timeline. | Open
4 | Communication | duplicate work | Team members independently complete the same documentation or feature | 3 | 3 | 2 | 9 | team leader and all members | end of class | Keep doing what we're doing. Having each team member give a small status update at each meeting is helpful to avoid duplicate work. | Work has been split among team members. Distinct tasks and areas have prevented this from being an issue. | Open
7 | Communication | inconsistent work | Variable output from week to week | 3 | 3 | 3 | 10 | All | end of class | Check in during team meetings, make sure everyone has support if life comes up or if that week's tasks are particularly time consuming. | No issues so far | Open
13 | Management | lack of management skills | Let's be real, we're not C-suite executives. Unless you are, in which case my apologies! | 3 | 3 | 3 | 11 | All | end of class | Do our best! Communicate constantly, be respectful, open, and honest | Team is working well together to control scope and manage distribution of responsibilities. No management issues | Open
18 | Technology competence | Not familiar with Git |  | 1 | 4 | 2 | 12 | Configuration leader and all team members | Start/middle of iteration 1 | Monitor commits and keep branches clean by following branching strategy laid out by config leader. | So far so good. As a team, our repo is a little messy. But everyone is familiar with Git and has pushed code successfully. | Open
3 | Personnel | Lack of motivation or responsibility | One or more team members have not been given engaging or important tasks | 1 | 4 | 3 |  | All team members | end of class | Check in each week with each team member. How are your tasks going? Is there enough to do? Do you need support? | All team members are involved and working to help the group succeed | Closed
8 | Requirements | unclear requirements | Features are not described in explicit detail. Not enough information to begin implementation | 2 | 4 | 2 |  | Requirements leader and all team members | middle of iteration 1 | Send out user surveys to gain insight into potential features. Discuss and refine requirements in meetings during weeks 1 and 2 | All planned requirements are detailed and clear. | Closed
5 | Communication | worked on wrong components | Tasks were not detailed enough, work completed for wrong area of the project | 2 | 4 | 3 |  | All | End of iteration 1 | Use team meetings and Jira tasks to ensure that everyone's responsibilities are clear | Everybody has their assigned areas and tasks are clear. No confusion as to who is working on what. | Closed
2 | Personnel | add new team members |  | 1 | 2 | 2 |  | All team members | 2023-09-11 | Redefine scope and split current tasks if necessary | I hope we don't add more team members.... | Closed
1 | Personnel | Loss team members | One or more team members drop the class | 2 | 4 | 4 |  | team leader and all members |  | Redefine the project scope if necessary, and assign the tasks to other team members. | Nobody is dropping the class at this point | Closed
9 | Requirements | scope creep | Scope expands without being properly managed | 3 | 4 | 2 |  | Requirements leader and all team members | End of iteration 2 | Keep requirements focused on key features, discuss requirement additions at team meetings before officially adding them to the project | Scope creep is not an issue. If anything we'll be cutting scope | Closed
10 | Requirements | constant requirements changes | Requirements are updated repeatedly as new features are discussed/desired | 1 | 2 | 2 |  | Requirements leader and all team members | middle of iteration 1 | Cement base requirements during weeks 1 and 2. Develop plan for introducing future requirements changes. | Requirements are stable | Closed
15 | Technology competence | Not familiar with the programming language used | Using Javascript and Java | 1 | 4 | 3 |  | All team members | middle of iteration 1 | Research Java from perspective of assigned area if necessary | All team members are familiar with the programming languages. | Closed
17 | Technology competence | Other technology unfamiliarity |  | 1 | 2 | 1 |  | Configuration leader and all team members | End of iteration 0 | Confirm tools to be used during project, research any that we're unfamiliar with | No unfamiliarity with other technologies | Closed
6 | Communication | useless work | Work unrelated to project | 1 | 2 | 1 |  | All | End of iteration 0 | Discuss planned tasks together, update Jira to reflect current priorities | No work is being completed that's unrelated, but Jira needs to be updated more consistently | Closed
20 | Design and implementation | improper technology stack | [5 empty] | All |  |  |  | Closed