## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
| Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
19 | Design and implementation | Improper design | Poor architectural decisions leading to implementation, security, and reliability issues | 4 | 4 | 4 | 1 | Design/Implementation Leader and all team members | End of class | Do what we can until the end of iteration 2. For iteration 3, it's too late to make major design changes. | As we come to the end of iteration 3, it's clear that this risk was a big issue for our project. It looks like we will have to cut scope to reach the deadline with a functioning project. | Open
18 | Technology competence | Not familiar with Git |  | 3 | 4 | 3 | 2 | Configuration leader and all team members | end of class | Monitor commits and keep branches clean by following branching strategy laid out by config leader. | Git repo got messy through the end of iteration 2 into iteration 3. We have been making a concerted effort to delete unneeded branches and keep the repository in a consistent state. Still having a few issues. | Open
7 | Communication | inconsistent work | Variable output from week to week | 5 | 5 | 4 |  | All | end of iteration 3 | Check in during team meetings, make sure everyone has support if life comes up or if that week's tasks are particularly time consuming. | Inconsistent output from week to week has had a negative effect on the final product. This can serve as a reminder to all of us to check in earlier, be firm about requirements, and be more willing to pivot when a certain approach is not panning out. | Closed
14 | Technology competence | Not familiar with the framework used | Using Spring Boot and React | 2 | 2 | 4 |  | Design/Implementation Leader, security leader and all team members | end of iteration 3 | Team members who are more familiar with the frameworks should collaborate and provide assistance when they can. | By the end of iteration 3, all team members were able to become familiar with the frameworks and make contributions to either the Spring Boot or React code bases. | Closed
4 | Communication | duplicate work | Team members independently complete the same documentation or feature | 3 | 4 | 2 |  | team leader and all members | end of iteration 3 | Keep doing what we're doing. Having each team member give a small status update at each meeting is helpful to avoid duplicate work. | Work has been split among team members. Distinct tasks and areas have prevented this from being an issue for the most part. We did end up having a problem on the other end of the spectrum though. With only one person assigned to some areas, other work was blocked while waiting for feature delivery or debugging. | Closed
13 | Management | lack of management skills | Difficulty managing group personalities and steering the project in the right direction. Roadblocks not removed easily | 3 | 3 | 3 |  | All | end of iteration 3 | Do our best! Communicate constantly, be respectful, open, and honest | There have been some management issues throughout the project, not due to any one team member, but for the group as a whole. Looking back, there were several moments where our course could have been corrected by a strong voice advocating for best practices and holding people accountable. | Closed
12 | Management | improper planning | Ineffective meetings, missing key deliverables, unclear project direction | 5 | 5 | 5 |  | All | end of iteration 3 | Meet frequently and stay in contact over discord to align on key deliverables in remaining iterations. | A few key deliverables were missed, leading to rushed implementation at the last moments with little time for proper testing. | Closed
21 | Design and implementation | Messy code | Code with syntax errors and code smells | 3 | 3 | 2 |  | QA leader and all team members | End of iteration 3 | Refactor when necessary. Use Sonarqube for quality scanning | We were not able to integrate sonarqube into the pipeline, but use of maven plugins Spotless and Sonarlint allowed for code cleanup in the IDE. | Closed
11 | Management | improper task assignments | Wrong tasks assigned to wrong team members | 2 | 3 | 2 |  | Team leader and all members | end of class | Keep tasks in Jira organized, with clear goals for each team member during each iteration | At the end of iteration 3, team members had appropriate tasks and everyone contributed to their assigned areas. | Closed
22 | Testing | Not enough testing | self-explanatory | 1 | 3 | 3 |  | QA leader/security leader and all team members | end of iteration 3 | Continue writing unit and integration tests through iteration 3. Increase branch coverage as high as possible. | At the end of iteration 3, there are unit tests for most classes, and integration tests for all controllers. That brings our test coverage to approximately 90%. If we exclude domain classes which are mostly generated, test coverage will be above 90%. | Closed
16 | Technology competence | Not familiar with unit testing | Self explanatory | 2 | 2 | 3 |  | QA leader/security leader and all team members | end of iteration 3 | Review testing methodologies and testing metrics. Collaborate on testing when necessary. | Some issues with testing, but the team is working through them together | Closed
1 | Personnel | Loss team members | One or more team members drop the class | 2 | 4 | 4 |  | team leader and all members |  | Redefine the project scope if necessary, and assign the tasks to other team members. | Nobody is dropping the class at this point | Closed
2 | Personnel | add new team members |  | 1 | 2 | 2 |  | All team members | 2023-09-11 | Redefine scope and split current tasks if necessary | I hope we don't add more team members.... | Closed
3 | Personnel | Lack of motivation or responsibility | One or more team members have not been given engaging or important tasks | 1 | 4 | 3 |  | All team members | end of class | Check in each week with each team member. How are your tasks going? Is there enough to do? Do you need support? | All team members are involved and working to help the group succeed | Closed
5 | Communication | worked on wrong components | Tasks were not detailed enough, work completed for wrong area of the project | 2 | 4 | 3 |  | All | End of iteration 1 | Use team meetings and Jira tasks to ensure that everyone's responsibilities are clear | Everybody has their assigned areas and tasks are clear. No confusion as to who is working on what. | Closed
6 | Communication | useless work | Work unrelated to project | 1 | 2 | 1 |  | All | End of iteration 0 | Discuss planned tasks together, update Jira to reflect current priorities | No work is being completed that's unrelated, but Jira needs to be updated more consistently | Closed
8 | Requirements | unclear requirements | Features are not described in explicit detail. Not enough information to begin implementation | 2 | 4 | 2 |  | Requirements leader and all team members | middle of iteration 1 | Send out user surveys to gain insight into potential features. Discuss and refine requirements in meetings during weeks 1 and 2 | All planned requirements are detailed and clear. | Closed
9 | Requirements | scope creep | Scope expands without being properly managed | 3 | 4 | 2 |  | Requirements leader and all team members | End of iteration 2 | Keep requirements focused on key features, discuss requirement additions at team meetings before officially adding them to the project | Scope creep is not an issue. If anything we'll be cutting scope | Closed
10 | Requirements | constant requirements changes | Requirements are updated repeatedly as new features are discussed/desired | 1 | 2 | 2 |  | Requirements leader and all team members | middle of iteration 1 | Cement base requirements during weeks 1 and 2. Develop plan for introducing future requirements changes. | Requirements are stable | Closed
15 | Technology competence | Not familiar with the programming language used | Using Javascript and Java | 1 | 4 | 3 |  | All team members | middle of iteration 1 | Research Java from perspective of assigned area if necessary | All team members are familiar with the programming languages. | Closed
17 | Technology competence | Other technology unfamiliarity |  | 1 | 2 | 1 |  | Configuration leader and all team members | End of iteration 0 | Confirm tools to be used during project, research any that we're unfamiliar with | No unfamiliarity with other technologies | Closed
20 | Design and implementation | improper technology stack | [5 empty] | All |  |  |  | Closed
23 | Integration and deployment | Not enough time for integration and deployment |  | 4 | 4 | 4 |  | Build/config leader and all | Closed | App is up on Heroku as of end of iteration 3 | Excellent work by config leader to get app up and running on Heroku. | Closed